## Project overview - contacts
Proprietary and Confidential |  | DIA for <Element>
Program/Project: <STLA 12.3F2 >
Department: <department name>
File Name and Revision Level |  | Revision Date | Description of Changes
<filename & rev> |  | <Date> | Initial Release
STELLANTIS Contacts |  |  | Supplier Contacts
Safety Engineer | <Name> |  | Safety Engineer | <Name>
Funct. Safety Mgr. | <Name> |  | Safety Manager | XiaGuanghao
System Engineer | <Name> |  | Program Manager | <Name>
Design Responsible | <Name> |  | Engineering Manager | <Name>
Design/Release Engr. | <Name> |  | System Engineer | <Name>
Quality/Reliability Engr. | <Name> |  | HW Design Engineer | <Name>
<Title> | <Name> |  | SW Design Engineer | <Name>
<Title> | <Name> |  | Quality Reliability | <Name>
<Title> | <Name> |  | <Title> | <Name>

## DIA V6.2
|  | Development Interface Agreement (DIA) |  |  |  |  | Component/Sub-System of Item: | STLA 12.3F2 |  | Stellantis Functional Safety Manager: | <Name>
|  | Is this a Presource DIA? | <Select> |  | RASI |  |  | Supplier Concurrence/Methods/Comments |  |  | Stellantis Comments | Global agreement status
ID | Reference : ISO 26262:2018 xF CS.00046/01 | Stellantis Policy & Procedure | Work Product Delivery Type (See Supplier Guidance for Definition) | Deliverable | Stellantis | <Supplier Name> | Primary "Responsible (Role) Name" | Supplier Concurrence to Stellantis Policy & Procedures | If "No" or "Partial", please provide alternative method and justification | Supplier Assumptions and Comments | Stellantis Assumptions and comments
Safety Management - All Development Phases
DIA-00-01 | All work products | The supplier shall apply the ISO-26262:2018 standard following at least the highly recommended characteristics of the associated ASIL per method tables. Stellantis reserves the right to request the supplier to provide evidence of compliance to the methods when clarification is required and justification of methods chosen. | 3- Not Applicable | General Requirement | A | R | FSM | Yes |  |  |  | <select>
DIA-00-02 | Verification Reviews/Reports | The Supplier shall conduct verification reviews according to the Safety Plan of the work products developed per the DIA. - Stellantis may request to review individual work products and supplier shall facilitate the review. - Stellantis may request to review reports of supplier internal process audit | 2- Short Version / Summary | Verification Review Reports | A | R | FSM | Yes |  | 2026/4/15:Guanghao:Review report is our internal design document, should be online audit, not short version delivery |  | <select>
DIA-02-5 | Overall Safety Management - 5.5.1 Organization-specific rules and processes for functional safety - 5.5.2 Evidence of competence management - 5.5.3 Evidence of a quality management system - 5.5.4 Identified safety anomaly reports, if applicable | Evidence of safety management include, but are not limited to the following: - Process Overview - Evidence of Continuous Process Improvement - Evidence of Quality Management System - Training and Competency Information | 2- Short Version Delivery / Summary - Delivery | Evidence of Safety Management | A | R | FSM | Yes |  | 2026/4/15:Guanghao: Internal process define functional safety process,procedure and corresponding templates. On-line audit, not short version delivery |  | <select>
DIA-02-6A | Project dependent safety management - 6.5.1 Impact analysis at the item level - 6.5.2 Impact analyses at element level, if applicable - | At the beginning of the-safety lifecycle the supplier shall perform an impact analysis. An impact analysis at the item level shall determine whether the item is a new development, a modification of an existing item, or an existing item with a modified environment. | 1 - Full Version Delivery | Impact Analysis | A | R | FSM | Not Applicable | 2026/4/15:Guanghao: No produced projects as benchmark,cannot perform impact analysis. |  |  | <select>
DIA-02-06B | Project dependent safety management - 6.5.3 Safety Plan | Timing for the deliverables in the DIA shall align with vehicle program milestones. Stellantis shall provide vehicle program milestones to the supplier. | 2- Short Version Delivery / Summary - Delivery | Vehicle Program Milestones | R | I | OEM | Yes |  |  |  | <select>
DIA-02-06C | Safety management during the concept phase and the product development - 6.5.3 Safety plan | The supplier shall develop a safety plan in accordance with the applicable vehicle program milestones. The initial safety plan and any changes to the safety plan require alignment and agreement with Stellantis. The safety plan shall include all planned deliverables, verification reviews and confirmation reviews. During the planning phase, the Supplier and Stellantis shall agree to a Functional Safety Assessment Plan for the project. An internal functional safety assessment by the supplier is sufficient as long as the supplier can provide the required level of independence and competency for the assessor(s). Stellantis reserves the right to request an external assessment based on several factors including supplier performance. | 1 - Full Version Delivery | Safety Plan (Timing - Plan) | A | R | FSM | Yes |  |  |  | <select>
DIA-02-06D | Safety management during the concept phase and the product development - 6.5.5 Confirmation measure reports | The Supplier shall conduct confirmation reviews according to the Safety Plan of the work products developed per the DIA. - Stellantis may request to review individual work products and supplier shall facilitate the review. - Stellantis may request to review reports of supplier internal process audit - Stellantis may request to review the functional safety assessment report | 2 - Full Version Delivery | Confirmation Measure Reports | A | R | FSM | Yes |  | 2026/4/15:Guanghao:Internal design document, online audit, not full version delivery |  | <select>
DIA-02-06E | Safety management during the concept phase and the product development - 6.5.4 Safety case (SYSTEM SAFETY REPORT) | The Supplier shall support, according to the Safety Plan, delivery of final work products and supporting evidence for the Stellantis Safety Case in electronic format. The report shall include document name and storage location of the final work products which are considered proprietary to supplier and can be easily audited by Stellantis. "Evidence, reports...etc." shall contain sufficient content which is acceptable for positive justification and support in meeting the goal of the deliverables and metrics required in parts 4, 5 and 6 of the ISO-26262:2018 standard and this document. | 1 - Full Version Delivery | Safety Case | A | R | FSM | Yes |  |  |  | <select>
DIA-02-06F | Safety management during the concept phase and the product development - 6.5.6 Release for production report | The supplier shall provide documentation indicating their item / element meets criteria for the applicable road release(s) from development to production. CAT 1: Restricted system release and is recommended for bench tests only. CAT 2: Restricted system release and is recommended for use in vehicles on test tracks with qualified test drivers. CAT 3: Restricted system release and is recommended for use in vehicles in all driving conditions, driven by qualified drivers (but excluding without any misuse tests on public roads). CAT 4: Restricted system release and is recommended for use in vehicles in mass testing including convenience and robustness tests for public roads. CAT 5: Unrestricted system release. | 1 - Full Version Delivery | Road Release Safety Report(s) | A | R | FSM | Yes |  | 2026/4/15:Guanghao:TIANMA will provide CAT level in each software release acceptance |  | <select>
|  | Supplier shall provide - Evidence for confidence in the achievement of functional safety (Confirmation reviews, Audit and Assessment reports) - Results of the functional safety assessment report, with the recommendation - Release for production report shall comply with ISO 26262-8:2018, part 2, 6.4.13.4 - Report including the calibration data and hardware and software baselines shall be provided for release | 1 - Full Version Delivery | Release for production report | A | R | FSM | Yes |  | 2026/4/15:Guanghao:The production release report is part of out safety case report |  | <select>
Part 3: Concept Phase
DIA-03-5 | Item definition - 5.5.1 Item definition | The supplier shall provide support, when needed, in areas of its expertise. | 3- Not Applicable | Item Definition - Not Provided to Supplier | R | I | OEM | Yes |  |  |  | <select>
DIA-03-6 | Hazard analysis and risk assessment - 6.5.1 Hazard analysis and risk assessment report - 6.5.2 Verification report of the hazard analysis and risk assessment | The supplier shall provide support, when needed, in areas of its expertise. | 3- Not Applicable | HARA - Not provided to supplier, only Safety Goals and ASIL | R | I | OEM | Yes |  |  |  | <select>
DIA-03-7 | Functional safety concept Functional Safety - 7.5.1 Functional safety concept - 7.5.2 Verification report of the functional safety concept | Stellantis shall provide Functional Safety Requirements with including hazard metrics definition, applicable to the sourced element to the supplier. The supplier shall provide support, when needed, in areas of its expertise. | 2- Short Version Delivery / Summary - Delivery | Functional Safety Concept | R | S | OEM | Yes |  |  |  | <select>
Part 4: Product Development : Vehicle / Item level
DIA-04A-06 | Technical Safety Concept - 6.5.1 Technical safety requirements specification - 6.5.2 Technical safety concept | Stellantis shall provide Technical Safety Requirements with including hazard metrics definition, applicable to the sourced element to the supplier. The supplier shall provide support, when needed, in areas of its expertise. | 2- Short Version Delivery / Summary - Delivery | Technical Safety Concept | R | S | OEM | Yes |  |  |  | <select>
DIA-04A-07 | Item integration and testing - Vehicle Level - 7.5.1 Integration and test strategy - 7.5.2 Integration and test report | Stellantis, with support from the Supplier, shall develop the vehicle level verification and validation plan. | 3- Not Applicable | Vehicle Verification and Validation Plan | R | S | OEM | Yes |  |  |  | <select>
DIA-04A-08 | Safety validation - Vehicle Level - 8.5.1 Safety validation specification - 8.5.2 Safety validation report | Stellantis, with support from the Supplier, shall develop the vehicle level verification and validation specifications. | 3- Not Applicable | Vehicle Verification and Validation Specification(s) | R | S | OEM | Yes |  |  |  | <select>
Part 4: Product Development: Element level (ECU)
DIA-04B-06A | Technical Safety Concept - 6.5.1 Technical safety requirements | The supplier shall decompose each Stellantis Technical Safety Requirement into hardware, software and interface requirements. The supplier shall demonstrate bi-directional traceability by providing formalized safety requirements to Stellantis. | 1 - Full Version Delivery | Requirements Traceability Matrix | A | R | FSM | Yes |  | 2026/4/15:Guanghao:TIANMA will provide the requirements traceablity matrix of FSR,TSR,HSR,SSR(only requirement id, more detail information need to review online) |  | <select>
DIA-04B-06B | Technical Safety Concept - 6.5.2 Technical safety concept resulting from safety requirements - 6.5.3 System architectural design specification - 6.5.4 Hardware-software interface (HSI) specification | The supplier shall demonstrate system architectural design and HSI satisfy the technical safety requirements.. | 2 - Full Version Delivery | Technical Safety Concept | A | R | FSM | Yes |  | 2026/4/15:Guanghao:TIANMA will provide short version TSC, online review full version |  | <select>
DIA-04B-06C | Technical Safety Concept - 6.5.7 Safety analyses report | The supplier shall deliver evidences that all Safety analyses have been performed along with an associated report. The supplier evidence shall identify any residual risk. Types of Analysis are dependent on the ASILs the product has to meet. Supplier shall supply histogram of risk reduction throughout the design process. In addition the delivery of this summary shall follow Stellantis guidelines. See example on tab 'FMEA Risk'. | 4 - Full Version Delivery | Safety Analysis Reports | A | R | FSM | Yes |  | 2026/4/15:Guanghao:TIANMA will provide short version safety analysis reports |  | <select>
DIA-04B-07 | Item integration and testing - 7.5.1 Integration and test strategy | The supplier shall deliver the verification and validation (V&V) plan for the entire lifecycle (V-Model) of the product and shall comply with ISO-26262:2018 Part 8 Clause 9. For example: test strategy, test methods definition, test results on each sample, non-regression test strategy, and traceability to safety requirements. Note: The V&V Plans may include, but are not limited to: - Requirements Testing - Fault Injection Testing - Back to back testing - Electrical Testing (voltage ranges, spikes, dropouts, etc.) - Life & durability testing - SW function & call coverage testing - Environmental & stress testing | 1 - Full Version Delivery | Item / ECU Verification and Validation Plan(s) | A | R | SV | Yes |  | 2026/4/15:Guanghao:TIANMA will be responsible for ECU level verification, and only online audit, not full version delivery |  | <select>
DIA-04B-08A | Safety validation - Item / ECU Level - 8.5.1 Safety validation specification | The verification and test specifications shall be developed in accordance to ISO-26262:2018 Part 8 Clause 9. The verification specification shall specify the methods, examples include but not limited to checklists, simulations, test cases, test data or test objects. The specification of test cases shall include unique identification, preconditions, configurations, environmental conditions, input data, and expected behavior. | 2- Short Version Delivery / Summary - Delivery | Item / ECU Verification and Validation Specification(s) | A | R | SV | Yes |  | 2026/4/15:Guanghao:TIANMA will be responsible for ECU level verification, and only online audit, not short version delivery |  | <select>
DIA-04B-08B | Safety validation - Item / ECU Level - 6.5.6 System Architectural Design and HSI Verification Report - 7.5.2 Integration and test report - 8.5.2 Safety validation report | The supplier has to deliver evidences, through a report, that verification and testing has been performed accordingly to ISO-26262:2018 Part 8 Clause 9 .The reports shall demonstrate the verification and test results of the following: - System Architecture Design and HSI - Item / ECU Integration - Item / ECU | 1 - Full Version Delivery | Item / ECU Verification and Validation Report(s) | A | R | SV | Yes |  | 2026/4/15:Guanghao:TIANMA will be responsible for ECU level verification, and TIANMA will provide summary test result of our internal TSR, not full version delivery |  | <select>
Part 5: Product Development: Hardware level
DIA-05-06 | Specification of hardware safety requirements - 6.5.1 Hardware safety requirements specification - 6.5.2 Hardware-software interface specification (HSI) (refined) - 6.5.3 Hardware safety requirements verification report | Supplier shall provide reviews of all HW Safety Requirements and HSI Specifications upon request to meet the Stellantis Safety Concept and TSRs. Stellantis to approve. The specification reviews may include, but are not limited to: - HW architecture requirements (Operating Modes/Models) - UML Model Format is acceptable. - Requirements to ensure independence between HW elements. - HW environment and EMC - Mapping of HW I/O, sensors, actuators, etc. to SW low level interface - Diagnostic features and fault storage necessary for service & field monitoring - Calibrations - HW resource usage, timing requirements/constraints | 2- Short Version Delivery / Summary - Delivery | HW Safety Requirements and HSI Specification | A | R | HW | Yes |  | 2026/4/15:Guanghao:Internal design document, on-line audit, not short version delivery |  | <select>
DIA-05-07 | Hardware Design - 7.5.1 Hardware design specification - 7.5.2 Hardware safety analysis - 7.5.3 Hardware design verification report - 7.5.4 Specification of requirements related to production, operation, service and decommissioning | Supplier shall provide sufficient detail for the HW Functional Safety designs upon request to demonstrate that the Stellantis Safety Concept and TSRs are achieved and that hardware is free from unintended behavior with respect to its functional design intent . Stellantis to approve. The HW Design documents reviews may include, but are not limited to: - HW Architecture Design - HW circuit/component design drawings/layouts/schematics - HW Models and/or simulations - Design studies/justification documents - Worst Case Circuit Analysis (Operational Margins) - HW Safety analyses (e.g. FMEDA, FTA, PMHF evaluation) | 2- Short Version Delivery / Summary - Delivery | HW Design Documents | A | R | HW | Yes |  | 2026/4/15:Guanghao:Internal design document, on-line audit, not short version delivery |  | <select>
DIA-05-08 | Evaluation of the HW Architectural Metrics - 8.5.1 Analysis of the effectiveness of the architecture of the item to cope with the random hardware failures - 8.5.2 Verification review report of evaluation of the effectiveness of the architecture of the item to cope with the random hardware failures resulting | Supplier shall demonstrate HW capability (SPFM and LFM) by performing FMEDA for ASIL B (if requested by Stellantis) and for ASIL C and ASIL D safety goals. - Supplier shall perform FMEDA if their element is allocated with a decomposed requirement from ASIL C or ASIL D safety goals. For example: ASIL C(D), ASIL B(D), ASIL A(D) , ASIL B(C), ASIL A(C). - Supplier shall provide evidence of effectiveness of the safety mechanism at detecting faults. | 1 - Full Version Delivery | FMEDA Report | A | R | HW | Yes |  | 2026/4/15:Guanghao:TIANMA can provide the FMEDA result. |  | <select>
|  |  | 2- Short Version Delivery / Summary - Delivery | FMEDA | A | R | HW | Yes |  | 2026/4/15:Guanghao:TIANMA can provide the FMEDA result. However, for the complete FMEDA, only online audit is available |  | <select>
DIA-05-09 | Evaluation of safety goal violations due to random HW failures - 9.5.1 Analysis of safety goal violations due to random hardware failures - 9.5.2 Specification of dedicated measures for hardware - 9.5.3 Verification review report of evaluation of safety goal violations due to random hardware failures | Supplier shall demonstrate HW capability (PMHF) by performing FMEDA for ASIL B (if requested by Stellantis) and for ASIL C and ASIL D safety goals. - Supplier shall perform FMEDA if their element is allocated with a decomposed requirement from ASIL C or ASIL D safety goals. For example: ASIL C(D), ASIL B(D), ASIL A(D) , ASIL B(C), ASIL A(C). - Supplier shall provide evidence of the effectiveness of the safety mechanism at detecting faults. - The FIT budget shall be mutually agreed between Stellantis and the supplier. | 1 - Full Version Delivery | FMEDA Report | A | R | HW | Yes |  | 2026/4/15:Guanghao:TIANMA can provide the FMEDA result. |  | <select>
|  |  | 2- Short Version Delivery / Summary - Delivery | FMEDA | A | R | HW | Yes |  | 2026/4/15:Guanghao:TIANMA can provide the FMEDA result. However, for the complete FMEDA, only online audit is available |  | <select>
DIA-05-10A | Hardware Verification and Test - 10.5.1 Hardware integration and verification specification | The verification and test specifications shall be developed in accordance to ISO-26262:2018 Part 8 Clause 9. The verification specification shall specify the methods, examples include but not limited to checklists, simulations, test cases, test data or test objects. The specification of test cases shall include unique identification, preconditions, configurations, environmental conditions, input data, and expected behavior. | 2- Short Version Delivery / Summary - Delivery | Hardware Integration Verification Specification(s) | A | R | HW | Yes |  | 2026/4/15:Guanghao:Internal design document, on-line audit, not short version delivery |  | <select>
DIA-05-10B | Hardware Verification Reports - 6.5.3 Hardware safety requirements verification report 7.5.3 Hardware design verification report - 10.5.2 Hardware integration and verification report | The supplier has to deliver evidences, through a report, that verification and testing has been performed accordingly to ISO-26262:2018 Part 8 Clause 9 .The reports shall demonstrate the verification and test results of the following: - Hardware Safety Requirements - Hardware Design - Hardware Integration | 1 - Full Version Delivery | Hardware Integration Verification Report(s) | A | R | HW | Yes |  | 2026/4/15:Guanghao:Internal design document, on-line audit, not full version delivery |  | <select>
Part 6: Product Development: Software Level
DIA-06-00 | General topics for the product development at the software level - 5.5.1 Documentation of the software development environment resulting from requirements | Stellantis uses a detailed follow-up questionnaire, "DMOV_ELE06_0050", to check supplier adherence to: • ISO 26262:2018 “Road Vehicles – Functional Safety” • Basic cybersecurity principles • Software Technical Quality rules based on project lessons learned The questionnaire is completed by the supplier and its status is assessed by Stellantis. Project status is monitored throughout the course of the project and shall be included in the component safety case for safety related components. The execution of supplier processes and technical measures will be assessed based on conformity, implementation and verification/validation. The supplier may be required to demonstrate implementation of their processes. Stellantis reserves the right to audit the supplier’s A-SPICE level and its safety and cybersecurity processes. | 1 - Full Version Delivery | DMOV_ELE06_0050 | A | R | SW | Yes |  |  |  | <select>
DIA-06-06 | Specification of software safety requirements - 6.5.1 Software safety requirements specification - 6.5.2 Hardware-software interface (HSI) specification (refined) - C.5.1 Configuration data specification - C.5.2 Calibration data specification | Supplier shall provide reviews of SW Safety Requirements upon request to demonstrate the software safety requirements meet Stellantis TSRs. | 2- Short Version Delivery / Summary - Delivery | Specification of Software Safety Requirements | A | R | SW | Yes |  | 2026/4/15:Guanghao:Internal design document, on-line audit, not short version delivery |  | <select>
DIA-06-07 | Software architectural design - 7.5.1 Software architectural design specification - 7.5.2 Safety analysis report - 7.5.3 Dependent failures analysis report - C.5.7 Software architectural design specification (refined) - C.5.8 Documentation of the software development environment | Supplier shall provide sufficient detail for the SW FS designs upon request to demonstrate that the Stellantis Safety Concept and TSRs are achieved and that the software is free from unintended behavior with respect to its functional design intent. The SW Design documents shall include, but are not limited to: - SW Architecture design - SW static & dynamic design - SW re-use & purchased/licensed SW - SW resource usage & timing study - SW Coding Rules/Notation Methods - SW Diagnostic design - Dependent Failure Analysis | 2- Short Version Delivery / Summary - Delivery | SW Design Documents | A | R | SW | Yes |  | 2026/4/15:Guanghao:Internal design document, on-line audit, not short version delivery |  | <select>
DIA-06-08 | Software unit design and implementation - 8.5.1 Software unit design specification - 8.5.2 Software unit implementation - 10.5.2 Embedded software - C.5.3 Configuration data - C.5.4 Calibration data | Stellantis may request to review supplier software implementation documentation: - Software design specifications - Software safety requirements traceability matrix | 2- Short Version Delivery / Summary - Delivery | Software Implementation Documentation | A | R | SW | Yes |  | 2026/4/15:Guanghao:Internal design document, on-line audit, not short version delivery |  | <select>
DIA-06-09 | Software Verification Specifications - 9.5.1 Software verification specification - 10.5.1 Software verification specification (refined) - 11.5.1 Software verification specification (refined) - C.5.5 Verification specification (refined) | The verification and test specifications shall be developed in accordance to ISO-26262:2018 Part 8 Clause 9. The verification specification shall specify the methods, examples include but not limited to checklists, simulations, test cases, test data or test objects. The specification of test cases shall include unique identification, preconditions, configurations, environmental conditions, input data, and expected behavior. | 2- Short Version Delivery / Summary - Delivery | Software Verification Specification(s) | A | R | SW | Yes |  | 2026/4/15:Guanghao:Internal design document, on-line audit, not short version delivery |  | <select>
DIA-06-10 | Software Verification Reports - 6.5.3 Software verification report - 7.5.4 Software verification report - 9.5.2 Software verification report (refined) - 10.5.3 Software verification report (refined) - 11.5.2 Software verification report (refined) - C.5.6 Verification report (refined) | The supplier has to deliver evidences, through a report, that verification and testing has been performed accordingly to ISO-26262:2018 Part 8 Clause 9 .The reports shall demonstrate the verification and test results of the following: - Software Safety Requirements - Software Architectural Design - Software Units - Software Integration - Embedded Software - Configuration and Calibration Data | 1 - Full Version Delivery | Software Verification Report(s) | A | R | SW | Yes |  | 2026/4/15:Guanghao:Internal design document, on-line audit, not full version delivery |  | <select>
Part 7: Production and operation
DIA-07-05 | Planning for production, operation, service and decommissioning - 5.5.1 Safety-related content of the production plan - 5.5.2 Safety-related content of the production control plan, including the test plan - 5.5.3 Producibility requirements specification - 5.5.4 Production process capability report | The Supplier shall review the safety related sections of the Stellantis PFMEA and Control Plans. Supplier to report comments/improvements. (e.g. Calibration procedures…etc.) | 2- Short Version Delivery / Summary - Delivery | PFMEA, Control Plans | A | R | NPI | Yes |  | 2026/4/15:Guanghao:Internal design document, on-line audit, not short version delivery |  | <select>
DIA-07-06 | Production - 6.5.1 Control measures report - 6.5.2 Production process capability report | The Supplier shall share the safety related sections of their PFMEA and Control Plans. Proof of In-line and EOL testing safety related portions of the Element (Pass/Fail criteria demonstrated). Stellantis to approve. The Supplier shall provide to Stellantis complementary Control plans for Stellantis manufacturing process if needed. | 2- Short Version Delivery / Summary - Delivery | PFMEA, Control Plans | A | R | NPI | Yes |  | 2026/4/15:Guanghao:Internal design document, on-line audit, not short version delivery |  | <select>
DIA-07-07 | Operation, service, and decommissioning - 7.5.1 Field observation instructions | The Supplier shall adhere to PS-11346 WARRANTY RETURNED PARTS TESTING AND ANALYSIS PROCEDURES. Stellantis to approve process and reports. | 2- Short Version Delivery / Summary - Delivery | Evidence of field monitoring | A | R | CQ | Yes |  |  |  | <select>
DIA-07-05A | Operation, service, and decommissioning - 5.5.5 Safety-related content of the service plan - 5.5.6 Safety-related content of the service instructions | The Supplier shall review the safety related sections of the Service Manual and procedures upon request from Stellantis. Supplier to report comments/improvements. (e.g. Calibration procedures…etc.) | 1 - Full Version Delivery | Service Manual Review Report (Relevant Sections Upon Request) | A | R | FSM | Yes |  | 2026/4/15:Guanghao:TIANMA can support stellantis to review the safety related sections of the Service Manual and procedures if it is applicable |  | <select>
DIA-07-05B | Operation, service, and decommissioning - 5.5.7 Safety-related content of the information made available to the user | The Supplier shall review the safety related sections of the Owner's Manual upon request from Stellantis. Supplier to report comments/improvements. | 1 - Full Version Delivery | Owners Manual Review Report (Relevant Sections Upon Request) | A | R | FSM | Yes |  | 2026/4/15:Guanghao:TIANMA can support stellantis to review the safety related sections of the Owner's Manual if it is applicable |  | <select>
DIA-07-05C | Vehicle Decommissioning - 5.5.8 Safety-related content of the decommissioning instructions - 5.5.9 Operation, service and decommissioning requirements specification | The Supplier shall support and report any safety related recycling requirements and special handling/disposal requirements. | 1 - Full Version Delivery | Decommissioning Requirements Review Report (Relevant Sections Upon Request) | A | R | FSM | Yes |  | 2026/4/15:Guanghao:When it's applicable, it will be done |  | <select>
DIA-07-05D | Response to Vehicle Emergency - 5.5.10 Safety-related content of the rescue services instructions | The Supplier shall review the safety related Vehicle Information Labeling. Supplier to report comments/improvements. | 3 - Full Version Delivery | Vehicle Labels (Upon Request) | A | R | FSM | Yes |  | 2026/4/15:Guanghao:TIANMA can support stellantis to review the safety related Vehicle information Labeling if it is applicable |  | <select>
Part 8: Supporting Processes
DIA-08-05 | Interfaces within distributed Developments Note; supplier scope is for the suppliers of the supplier (tier 1+n) - 5.5.1 Supplier selection report - 5.5.2 Development interface agreement (DIA) - 5.5.3 Supplier's safety plan - 5.5.4 Functional safety assessment report - 5.5.5 Supplier agreement | Stellantis shall reserve the right to plan a safety assessment/audit with the supplier (tier 1 +n) and review any necessary work products. | 1 - Full Version Delivery | Supplier (tier 1 +n) Documents | A | R | Supplier (tier 1 +n) | Not Applicable | 2026/4/15:Guanghao:TIANMA don't have distributed developments in this project,it's not applicable |  |  | <select>
DIA-08-07 | Configuration Management - 7.5.1 Configuration management plan | Stellantis may request the supplier's configuration management plan. | 1 - Full Version Delivery | Configuration Management Plan | A | R | CM | Yes |  | 2026/4/15:Guanghao:Internal design document, on-line audit, not full version delivery |  | <select>
DIA-08-08 | Change Management - 8.5.1 Change management plan - 8.5.2 Change request - 8.5.3 Impact analysis and change request plan - 8.5.4 Change report | All Supplier work products shall be under change and configuration management and shall be traceable to appropriate requirements specification(s) and aligned with safety plan Supplier shall create/submit a traceability report in each phase of development. After initial safety case is approved, the supplier shall inform the Stellantis safety team of changes not driven by Stellantis functional requirements. These changes could result from quality issues or IC shortages. The supplier shall perform impact analysis and communicate to Stellantis planned updates to safety artifacts. | 1 - Full Version Delivery | Change Management Plan | A | R | PM | Yes |  | 2026/4/15:Guanghao:Internal design document, on-line audit, not full version delivery |  | <select>
DIA-08-10 | Documentation management - 10.5.1 Documentation management plan - 10.5.2 Documentation guideline requirements | Stellantis may request the supplier's document management plan. | 1 - Full Version Delivery | Documentation Management Plan | A | R | CM | Yes |  | 2026/4/15:Guanghao:Internal design document, on-line audit, not full version delivery |  | <select>
DIA-08-11 | Confidence in the Use of SW Tools - 11.5.1 Software tool criteria evaluation report - 11.5.2 Software tool qualification report | SW Tool Requirements, Confidence & compatibility report(s) per ISO-26262:2018 recommendations. | 1 - Full Version Delivery | Software Tool Qualification Report | A | R | FSM | Yes |  | 2026/4/15:Guanghao:Internal design document, on-line audit, not full version delivery |  | <select>
DIA-08-12 | Qualification of SW Components - 12.5.1 Software component documentation - 12.5.2 Software component qualification report - 12.5.3 Software component qualification verification report | Stellantis may request software qualification reports. | 1 - Full Version Delivery | Software Qualification Verification Report | A | R | SV | Yes |  | 2026/4/15:Guanghao:Internal design document, on-line audit, not full version delivery |  | <select>
DIA-08-13 | Evaluation of HW elements - 13.5.1 Hardware element evaluation plan - 13.5.2 Hardware element test plan - 13.5.3 Hardware element evaluation report for hardware elements | Stellantis may request Hardware element evaluation report. | 1 - Full Version Delivery | Hardware element evaluation report | A | R | HW | Yes |  | 2026/4/15:Guanghao:Internal design document, on-line audit, not full version delivery |  | <select>
DIA-08-14 | Proven in Use Argument - 14.5.1 Description of candidate for proven in use argument - 14.5.2 Proven in use analysis reports | Proven in Use Argument will be considered on a case by case basis. Acceptance will require full disclosure and documentation demonstrating the proven in use argument. | 1 - Full Version Delivery | Proven In Use Argument | A | R | FSM | Not Applicable | 2026/4/15:Guanghao:No reuse for this project |  |  | <select>
Part 9: ASIL-oriented and safety-oriented analyses
DIA-09-05 | Requirements decomposition with respect to ASIL tailoring - 5.5.1 Update of architectural information - 5.5.2 Update of ASIL as attribute of safety requirements and elements | If ASIL decomposition is applied, the supplier shall ensure that a safety requirement is decomposed into redundant safety requirements allocated to sufficiently independent design elements. ASIL decomposition shall comply with the permitted ASIL decomposition schemas. Stellantis may request to review any ASIL decomposition applied by the supplier. | 2- Short Version Delivery / Summary - Delivery | ASIL Decomposition | A | R | FSM | Not Applicable | 2026/4/15:Guanghao:Not applicable for this ASILB project |  |  | <select>
DIA-09-06 | Criteria for coexistence of elements - 6.5.1 Update of the ASIL attribute of the sub-elements of the element | Stellantis may request to review criteria of coexistence between safety related elements and non-safety related elements. This also includes elements having mixed ASILs. | 2- Short Version Delivery / Summary - Delivery | Criteria of Coexistence | A | R | FSM | Yes | 2026/4/15:Guanghao:It will be analyzed in the DFA |  |  | <select>
DIA-09-07 | Analysis of dependent failures - 7.5.1 Dependent Failures Analysis - 7.5.2 Dependent Failures Analysis Verification Report | Stellantis may request to review supplier's dependent failure analysis. a) to confirm that a required independence or freedom from interference is sufficiently achieved in the design by analyzing their potential causes or initiators; and b) to define safety measures to mitigate plausible dependent failures, if necessary. | 2- Short Version Delivery / Summary - Delivery | Dependent Failure Analysis | A | R | SW | Yes |  |  |  | <select>
[6 empty] | R | Responsible for activity/deliverable | Yes
|  |  | 1 - Full Version Delivery |  |  | A | Approves final deliverable | No
|  |  | 2- Short Version Delivery / Summary - Delivery |  |  | S | Supports development of deliverable | Not Applicable
|  |  | 3- Not Applicable |  |  | I | Informed (view) final deliverable | <select>
<select>

## DIA V5 (hidden)
|  | Development Interface Agreement (DIA) | [5 empty] | Component/Sub-System of Item: | <Project> |  | Stellantis Functional Safety Manager: | <Name>
|  | Is this a Presource DIA? | <Select> |  |  | RASI |  |  | Supplier Concurrence/Methods/Comments |  |  | Stellantis Comments | Global agreement status
ID | Reference : ISO 26262:2018 xF CS.00046/01 | Stellantis Policy & Procedure | Data exchange method (delivered, screen sharing, at premises) | Deliverable | Records & Document Exchange or Review | Stellantis | <Supplier Name> | Primary "Responsible (Role) | Supplier Concurrence to Stellantis Policy & Procedures | If "No" or "Partial", please provide alternative method and justification | Supplier Assumptions and Comments | Stellantis Assumptions and comments
General Requirements (Work Products Across All Development Phases)
DIA-00-01 | All workproducts | It is required to apply the ISO 26262 standard following at least the “highly recommended (++)" methods of the tables. | [5 empty] | <Name> | <select> |  |  |  | <select>
DIA-00-02 | All workproducts | All Work Products under supplier's responsibility are at least available at the supplier premises. | Work Product Submission Level: 1 - Full Version Delivery 2- Short Version Delivery / Summary - Delivery of Synthesis or Relevant Extracted Information 3 - Review at Supplier Premise 4- NA |  |  |  |  | <Name> | <select> |  |  |  | <select>
DIA-00-03 | All workproducts | By default, all Work Products delivered to Stellantis shall be in MS Office or PDF/A Family format. | [5 empty] | <Name> | <select> |  |  |  | <select>
DIA-00-04 | All workproducts | The Supplier shall perform, according to their Safety Plan, Verification Reviews of their Work Products. The Supplier shall store Verification review reports in their safety case. |  |  | ex : Work Products for Review: Stellantis <--- Supplier Review Reports Stellantis ---> Supplier |  |  |  | <select> |  |  |  | <select>
DIA-02A-6 | Project dependent safety management section 6.5 part 2 - 6.5.1 Impact analysis at the item level - 6.5.2 Impact analyses at element level, if applicable - 6.5.3 Safety plan - 6.5.4 Safety case - 6.5.5 Confirmation measure reports - 6.5.6 Release for production report | Stellantis shall define the Project Safety Plan. Timing for deliverables in this DIA shall be specified in the Safety Plan. The Safety Plan shall be updated throughout the development lifecycle. In case of Stellantis initiated changes, Stellantis shall develop an Impact Analysis Report for each requested change and develop a work plan to update documentation/analysis for each approved requested change. | 1 - Full Version Delivery | Vehicle timing |  |  |  | <Name> | <select> |  |  |  | <select>
DIA-02A-6 | Project dependent safety management section 6.5 part 2 - 6.5.1 Impact analysis at the item level - 6.5.2 Impact analyses at element level, if applicable - 6.5.3 Safety plan - 6.5.4 Safety case - 6.5.5 Confirmation measure reports - 6.5.6 Release for production report | Stellantis shall define the Project Safety Plan. Timing for deliverables in this DIA shall be specified in the Safety Plan. The Safety Plan shall be updated throughout the development lifecycle. In case of Stellantis initiated changes, Stellantis shall develop an Impact Analysis Report for each requested change and develop a work plan to update documentation/analysis for each approved requested change. | 1 - Full Version Delivery | Vehicle timing |  |  |  | <Name> | <select> |  |  |  | <select>
DIA-02B-5 | Overall Safety Management - 5.5.1 Organization-specific rules and processes for functional safety - 5.5.2 Evidence of competence management - 5.5.3 Evidence of a quality management system - 5.5.4 Identified safety anomaly reports, if applicable | The supplier shall provide evidence to Stellantis, upon request, to demonstrate capability and maturity in Overall Safety Management (examples include: Process Overview, Evidence of Continuous Process Improvement, Evidence of Quality Management System, Training and Competency Information). | 2- Short Version Delivery / Summary - Delivery of Synthesis or Relevant Extracted Information | Safety Management Plan Quality Management System Evidence (IATF 16949 Cert) Competency Information | Stellantis <--- Supplier | A | R | <Name> | <select> |  |  |  | <select>
Part 2: Management of Functional Safety - Stellantis
DIA-02A-5 | Overall Safety Management - 5.5.1 Organization-specific rules and processes for functional safety - 5.5.2 Evidence of competence management - 5.5.3 Evidence of a quality management system - 5.5.4 Identified safety anomaly reports, if applicable |  | 4- Not Applicable | NA |  |  |  | <Name> | <select> |  |  |  | <select>
DIA-02A-6 | Project dependent safety management section 6.5 part 2 - 6.5.1 Impact analysis at the item level - 6.5.2 Impact analyses at element level, if applicable - 6.5.3 Safety plan - 6.5.4 Safety case - 6.5.5 Confirmation measure reports - 6.5.6 Release for production report | Stellantis shall define the Project Safety Plan. Timing for deliverables in this DIA shall be specified in the Safety Plan. The Safety Plan shall be updated throughout the development lifecycle. In case of Stellantis initiated changes, Stellantis shall develop an Impact Analysis Report for each requested change and develop a work plan to update documentation/analysis for each approved requested change. | 1 - Full Version Delivery | Vehicle timing |  |  |  | <Name> | <select> |  |  |  | <select>
DIA-02A-7 | Safety management after release for production - 7.5.1 Evidence of safety management regarding production, operation, service and decommissioning | [6 empty] | <Name> | <select> |  |  |  | <select>
Part 2: Management of Functional Safety - Supplier
DIA-02B-0 | Expectation for safety QM risks | Stellantis and the supplier shall mutually agree on the management of QM safety requirements. | [5 empty] | <Name> | <select> |  |  |  | <select>
DIA-02B-5 | Overall Safety Management - 5.5.1 Organization-specific rules and processes for functional safety - 5.5.2 Evidence of competence management - 5.5.3 Evidence of a quality management system - 5.5.4 Identified safety anomaly reports, if applicable | The supplier shall provide evidence to Stellantis, upon request, to demonstrate capability and maturity in Overall Safety Management (examples include: Process Overview, Evidence of Continuous Process Improvement, Evidence of Quality Management System, Training and Competency Information). | 2- Short Version Delivery / Summary - Delivery of Synthesis or Relevant Extracted Information | Safety Management Plan Quality Management System Evidence (IATF 16949 Cert) Competency Information | Stellantis <--- Supplier | A | R | <Name> | <select> |  |  |  | <select>
DIA-02B-6A | Project dependent safety management - 6.5.1 Impact analysis at the item level - 6.5.2 Impact analyses at element level, if applicable | If there is an Item modification to an existing production item/system or if there is a change to an item during the development lifecycle, the Supplier shall complete an Impact Analysis for the work products under their responsibility and provide an Impact Analysis report to Stellantis. | 1 - Full Version Delivery | Impact Analysis | Stellantis <--- Supplier | A | R | <Name> | <select> |  |  |  | <select>
DIA-02B-6B | Safety management during the concept phase and the product development - 6.5.3 Safety plan | The supplier shall develop a safety plan in accordance with the applicable vehicle program milestones. The initial safety plan and any changes to the safety plan require alignment and agreement with Stellantis. The safety plan shall include all planned deliverables, verification reviews and confirmation reviews. During the planning phase, the Supplier and Stellantis shall agree to a Functional Safety Assessment Plan for the project. An internal functional safety assessment by the supplier is sufficient as long as the supplier can provide the required level of independence and competency for the assessor(s). Stellantis reserves the right to request an external assessment based on several factors including supplier performance. | 1 - Full Version Delivery | Safety Plan (Timing - Plan) | Stellantis <--- Supplier | A | R | <Name> | <select> |  |  |  | <select>
DIA-02B-6C | Safety management during the concept phase and the product development - 6.5.4 Safety case (SYSTEM SAFETY REPORT) | The Supplier shall support, according to the Safety Plan, delivery of final work products and supporting evidence for the Stellantis Safety Case in electronic format. The report shall include a location (link) of the final work products which are considered proprietary to supplier and can be easily audited by Stellantis. "Evidence, reports...etc" shall contain sufficient content which is acceptable for positive justification and support in meeting the goal of the deliverables and metrics required in parts 4, 5 and 6 of the ISO26262 standard and this document. | 1 - Full Version Delivery | Safety Case | Stellantis <--- Supplier | A | R | <Name> | <select> |  |  |  | <select>
DIA-02B-06D | Safety management during the concept phase and the product development - 6.5.5 Confirmation measure reports | The Supplier shall conduct confirmation reviews according to the Safety Plan at the end of each phase of development throughout the Functional Safety lifecycle. Confirmation reviews shall consist of supplier defined proposal on what the supplier covers internally. - Review report to be communicated to Stellantis (findings, resolution, completion) - Report format to be mutually agreed between Stellantis and supplier. - Report to include evidence and documentation of independence and names of each reviewer. - Stellantis may request to review individual work products and supplier shall facilitate the review. - Stellantis may request to review reports of supplier internal process audit | 2 - Full Version Delivery | Confirmation Review Report | Stellantis <--- Supplier | I | R | <Name> | <select> |  |  |  | <select>
DIA-02B-06E | Safety management during the concept phase and the product development - 6.5.6 Release for production report | Supplier shall provide - Evidence for confidence in the achievement of functional safety (Confirmation reviews, Audit and Assessment reports) - Results of the functional safety assessment report, with the recommendation - Release for production report shall comply with ISO 26262-8:2018, part 2, 6.4.13.4 - Report including the calibration data and Hardware and software baselines shall be provided for release | 2 - Full Version Delivery | Release for production report | Stellantis <--- Supplier | A | R | <Name> | <select> |  |  |  | <select>
DIA-02B-7 | Safety management after release for production - 7.5.1 Evidence of safety management regarding production, operation, service and decommissioning) | Supplier shall provide Evidence of Field Monitoring and lessons learned management | 2- Short Version Delivery / Summary - Delivery of Synthesis or Relevant Extracted Information | Evidence of field monitoring | Stellantis <--- Supplier | I | R | <Name> | <select> |  |  |  | <select>
Part 3: Concept Phase
DIA-03-5 | Item definition - 5.5.1 Item definition | Stellantis and Supplier shall jointly agree on functionality of the elements of the Item that are the Supplier's responsibility As needed, only the relevant sections of the item definition shall be reviewed but will not be distributed to the supplier. The supplier shall provide support, when needed, in areas of its expertise. | 4- Not Applicable | NA | Not Applicable | R | I | <Name> | <select> |  |  |  | <select>
DIA-03-6 | Hazard analysis and risk assessment - 6.5.1 Hazard analysis and risk assessment report - 6.5.2 Verification report of the hazard analysis and risk assessment | According to the defined responsibility, the counterpart (Stellantis or supplier) shall provide support, when needed, in areas of its expertise. As needed, only the relevant sections of the HARA shall be reviewed but will not be distributed to the supplier. The supplier shall provide support, when needed, in areas of its expertise. | 4- Not Applicable | NA | Not Applicable | R | I | <Name> | <select> |  |  |  | <select>
DIA-03-7 | Functional safety concept Functional Safety - 7.5.1 Functional safety concept - 7.5.2 Verification report of the functional safety concept | According to the defined responsibility, the counterpart (Stellantis or supplier) The supplier shall provide support, when needed, in areas of its expertise. | 1 - Full Version Delivery | FSC | Stellantis ---> Supplier | R | I | <Name> | <select> |  |  |  | <select>
Part 4: Product Development : Vehicle / Item level
DIA-04A-00 | General topics for the product development at the system level |  |  |  |  | R | S | <Name> | <select> |  |  |  | <select>
DIA-04A-06 | Technical Safety Concept - 6.5.1 Technical safety requirements specification - 6.5.2 Technical safety concept - 6.5.3 System architectural design specification - 6.5.4 Hardware-software interface (HSI) specification - 6.5.5 Specification of requirements for production, operation, service and decommissioning - 6.5.6 Verification report for system architectural design, the hardwaresoftware interface (HSI) specification, the specification of requirements for production, operation, service and decommissioning, and the technical safety concept - 6.5.7 Safety analyses report | Stellantis shall provide Technical Safety Requirements with appropriate characterisation 8 including HW hazard metrics definition, applicable to the sourced element, to the Supplier. | 1 - Full Version Delivery | TSC | Stellantis <--- Supplier | R | I | <Name> | <select> |  |  |  | <select>
DIA-04A-07 | Item integration and testing - 7.5.1 Integration and test strategy - 7.5.2 Integration and test report | Stellantis, with support from the Supplier, shall develop the System and Vehicle level Verification and Validation (V&V) plans & methods. | 4- Not Applicable | NA | Not Applicable | R | S | <Name> | <select> |  |  |  | <select>
DIA-04A-08 | Safety validation - 8.5.1 Safety validation specification - 8.5.2 Safety validation report |  | 4- Not Applicable | NA | Not Applicable | R | <select> | <Name> | <select> |  |  |  | <select>
Part 4: Product Development: Element level (ECU)
DIA-04B-00 | General topics for the product development at the system level | Supplier shall organize and provide reviews of all system, H/W & S/W Safety Requirements and HSI Specifications necessary to meet the Stellantis Safety Concept and TSRs. |  |  |  | A | R | <Name> | <select> |  |  |  | <select>
DIA-04B-06A | Technical Safety Concept - 6.5.1 Technical safety requirements -> Bottom-up Requirements - 6.5.2 Technical safety concept - 6.5.3 System architectural design specification - 6.5.4 Hardware software interface (HSI) specification | The supplier shall decompose each Stellantis Technical Safety Requirement into hardware, software and interface requirements. The supplier shall demonstrate bi-directional traceability by providing formalized "bottom up" safety requirements to Stellantis. | 1 - Full Version Delivery | 1 - Requirements Traceability Matrix | Stellantis <--- Supplier | A | R | <Name> | <select> |  |  |  | <select>
DIA-04B-06B | Technical Safety Concept - 6.5.3 System architectural design specification | The supplier shall demonstrate allocation of TSRs to the syste |  |  |  | A | R | <Name> | <select> |  |  |  | <select>
DIA-04B-06C | Technical Safety Concept - 6.5.4 Hardware-software interface (HSI) specification | The supplier shall decompose Stellantis Technical Safety Requirements into hardware, software and interface requirements and maintain bi-directional demonstrable traceability as applicable. |  |  |  | A | R | <Name> | <select> |  |  |  | <select>
DIA-04B-06D | Technical Safety Concept - 6.5.5 Specification of requirements for production, operation, service and decommissioning | The supplier shall specify requirements, as applicable, to supplier and supplier supporting Stellantis production, operation, service and decommissioning activities. |  |  |  | A | R | <Name> | <select> |  |  |  | <select>
DIA-04B-06E | Technical Safety Concept - 6.5.6 Verification report for system architectural design, the hardwaresoftware interface (HSI) specification, the specification of requirements for production, operation, service and decommissioning, and the technical safety concept |  |  |  |  | A | R | <Name> | <select> |  |  |  | <select>
DIA-04B-06F | Technical Safety Concept - 6.5.7 Safety analyses report | The supplier shall deliver evidences that all Safety analyses have been performed along with an associated report. The supplier evidence shall identify any residual risk. Types of Analysis are dependent on the ASILs the product has to meet. Supplier shall supply histogram of risk reduction throughout the design process. In addition the delivery of this summary shall follow Stellantis guidelines. |  |  |  | A | R | <Name> | <select> |  |  |  | <select>
DIA-04B-07 | Item integration and testing - 7.5.1 Integration and test strategy - 7.5.2 Integration and test report | The supplier has to deliver evidences, through a report, that Safety integration and testing has been performed accordingly to ISO26262 expectations (for example: test strategy, test methods definition, test results on each sample, non-regression test strategy, and traceability to Safety requirements) Note: The V&V Plans may include, but are not limited to: - Requirements Testing - Fault Injection Testing - Electrical Testing (voltage ranges, spikes, dropouts, etc.) - Life & durability testing - SW function & call coverage testing - Environmental & stress testing |  | V&V Plan | Stellantis <--- Supplier | A | R | <Name> | <select> |  |  |  | <select>
DIA-04B-08A | Safety validation - 8.5.1 Safety validation specification | The supplier shall provide validation test plans and methods for mechanical, hardware and software verification/validation. The tests shall verify the correct implementation of technical safety requirement at mechanical, hardware and software level. | 1 - Full Version Delivery |  | Stellantis <--- Supplier | A | R | <Name> | <select> |  |  |  | <select>
DIA-04B-08B | Safety validation - 8.5.2 Safety validation report | The supplier shall provide reports that show the results of the mechanical, hardware and software validation tests. | 1 - Full Version Delivery |  | Stellantis <--- Supplier | A | R | <Name> | <select> |  |  |  | <select>
Part 5: Product Development: Hardware level
DIA-05-06 | Specification of hardware safety requirements - 6.5.1 Hardware safety requirements specification (including test and evaluation criteria and bottom-up requirements) - 6.5.2 Hardware-software interface specification (HSI) (refined) - 6.5.3 Hardware safety requirements verification report | Supplier shall provide reviews of all HW Safety Requirements and HSI Specifications necessary to meet the Stellantis Safety Concept and TSRs. Stellantis to approve. The specification reviews may include, but are not limited to: - HW architecture requirements (Operating Modes/Models) - UML Model Format is accepetable. - Requirements to ensure independence between HW elements. - HW environment and EMC - Mapping of HW I/O, sensors, actuators, etc. to SW low level interface - Diagnostic features and fault storage necessary for service & field monitoring - Calibrations - HW resource usage, timing requirements/constraints | 1 - Full Version Delivery | HW Safety Requirements and HSI Specification | Stellantis <--- Supplier |  |  | <Name> | <select> |  |  |  | <select>
DIA-05-07 | Hardware Design - 7.5.1 Hardware design specification - 7.5.2 Hardware safety analysis - 7.5.3 Hardware design verification report - 7.5.4 Specification of requirements related to production, operation, service and decommissioning | Supplier shall provide sufficient detail for the HW Functional Safety designs to demonstrate that the Stellantis Safety Concept and TSRs are achieved and that hardware is free from unintended behavior with respect to its functional design intent . Stellantis to approve. The HW Design documents reviews may include, but are not limited to: - HW Architecture Design - HW circuit/component design drawings/layouts/schematics - HW Models and/or simulations - Design studies/justification documents - Worst Case Circuit Analysis (Operational Margins) - HW Safety analyses (e.g. FMEDA, FTA, PMHF evaluation) | 1 - Full Version Delivery | HW Design Documents | Stellantis <--- Supplier |  |  | <Name> | <select> |  |  |  | <select>
DIA-05-08 | Evaluation of the HW Architectural Metrics - 8.5.1 Analysis of the effectiveness of the architecture of the item to cope with the random hardware failures - 8.5.2 Verification review report of evaluation of the effectiveness of the architecture of the item to cope with the random hardware failures resulting | Supplier shall demonstrate HW capability (SPFM and LFM) by performing FMEDA for ASIL B (if requested by Stellantis) and for ASIL C and ASIL D safety goals. - Supplier shall perform FMEDA if their element is allocated with a decomposed requirement from ASIL C or ASIL D safety goals. For example: ASIL B(D), ASIL B(C), ASIL A(D), ASIL A(C), ASIL QM(D), ASIL QM(C). - Supplier shall provide evidence of effectiveness of the safety mechanism at detecting faults. | 1 - Full Version Delivery | HW Metrics |  |  |  | <Name> | <select> |  |  |  | <select>
DIA-05-09 | Evaluation of safety goal violations due to random HW failures - 9.5.1 Analysis of safety goal violations due to random hardware failures - 9.5.2 Specification of dedicated measures for hardware - 9.5.3 Verification review report of evaluation of safety goal violations due to random hardware failures | Supplier shall demonstrate HW capability (PMHF) by performing FMEDA for ASIL B (if requested by Stellantis) and for ASIL C and ASIL D safety goals. - Supplier shall perform FMEDA if their element is allocated with a decomposed requirement from ASIL C or ASIL D safety goals. For example: ASIL B(D), ASIL B(C), ASIL A(D), ASIL A(C), ASIL QM(D), ASIL QM(C). - Supplier shall provide evidence of the effectiveness of the safety mechanism at detecting faults. - The FIT budget shall be mutually agreed between Stellantis and the supplier. | 1 - Full Version Delivery | HW Metrics |  |  |  | <Name> | <select> |  |  |  | <select>
DIA-05-10 | HW Integration and Testing - 10.5.1 Hardware integration and verification specification - 10.5.2 Hardware integration and verification report | V&V phase? | 1 - Full Version Delivery |  |  |  |  | <Name> | <select> |  |  |  | <select>
Part 6: Product Development: Software Level
DIA-06-05 | General topics for the product development at the software level - 5.5.1 Documentation of the software development environment resulting from requirements | Stellantis uses a detailed follow-up questionnaire, "DMOV_ELE06_0050", to check supplier adherence to: • ISO 26262:2018 “Road Vehicles – Functional Safety” • Basic cybersecurity principles • Software Technical Quality rules based on project lessons learned The questionnaire is completed by the supplier and its status is assessed by Stellantis. Project status is monitored throughout the course of the project and shall be included in the component safety case for safety related components. The execution of supplier processes and technical measures will be assessed based on conformity, implementation and verification/validation. The supplier may be required to demonstrate implementation of their processes. Stellantis reserves the right to audit the supplier’s A-SPICE level and its safety and cybersecurity processes. | 1 - Full Version Delivery | DMOV_ELE06_0050 | Stellantis <--- Supplier |  |  | <Name> | <select> |  |  |  | <select>
DIA-06-06 | Specification of software safety requirements - 6.5.1 Software safety requirements specification -> In particular, bottom-up requirements if any - 6.5.2 Hardware-software interface (HSI) specification (refined) -> In particular, bottom-up requirements if any - 6.5.3 Software verification report | Supplier shall provide appropriate detail for the SW FS designs to demonstrate that the FCA Safety Concept and TSRs are achieved and that the software is free from unintended behavior with respect to its functional design intent. FCA to approve. The SW Design documents shall include, but are not limited to: - SW Architecture design - SW static & dynamic design - SW re-use & purchased/licensed SW - SW resource usage & timing study - SW Coding Rules/Notation Methods - SW Diagnostic design - SW Tool Requirements, Confidence & compatibility report(s) Supplier shall provide their processes, evidences & reports Traceability Report | 1 - Full Version Delivery | Specicfication of SW Safety Requirements |  |  |  | <Name> | <select> |  |  |  | <select>
DIA-06-07 | Software architectural design - 7.5.1 Software architectural design specification - 7.5.2 Safety analysis report - 7.5.3 Dependent failures analysis report - 7.5.4 Software verification report |  | 1 - Full Version Delivery | SW Design Documents |  |  |  | <Name> | <select> |  |  |  | <select>
DIA-06-08 | Software unit design and implementation - 8.5.1 Software unit design specification - 8.5.2 Software unit implementation | [6 empty] | <Name> | <select> |  |  |  | <select>
DIA-06-09 | Software unit verification - 9.5.1 Software verification specification - 9.5.2 Software verification report (refined) | Recommend moving to V&V phase if decided.. | [5 empty] | <Name> | <select> |  |  |  | <select>
DIA-06-10 | Software integration and verification - 10.5.1 Software verification specification (refined) - 10.5.2 Embedded software - 10.5.3 Software verification report (refined) | [6 empty] | <Name> | <select> |  |  |  | <select>
DIA-06-11 | Testing of the embedded software - 11.5.1 Software verification specification (refined) - 11.5.2 Software verification report (refined) | [6 empty] | <Name> | <select> |  |  |  | <select>
DIA-06-C | Software configuration - C.5.1 Configuration data specification - C.5.2 Calibration data specification - C.5.3 Configuration data - C.5.4 Calibration data - C.5.5 Verification specification (refined) - C.5.6 Verification report (refined) - C.5.7 Software architectural design specification (refined) - C.5.8 Documentation of the software development environment (refined) | [6 empty] | <Name> | <select> |  |  |  | <select>
Part 7: Production and operation
DIA-07-05 | Planning for production, operation, service and decommissioning - 5.5.1 Safety-related content of the production plan - 5.5.2 Safety-related content of the production control plan, including the test plan - 5.5.3 Producibility requirements specification - 5.5.4 Production process capability report - 5.5.5 Safety-related content of the service plan - 5.5.6 Safety-related content of the service instructions - 5.5.7 Safety-related content of the information made available to the user - 5.5.8 Safety-related content of the decommissioning instructions - 5.5.9 Operation, service and decommissioning requirements specification - 5.5.10 Safety-related content of the rescue services instructions | [6 empty] | <Name> | <select> |  |  |  | <select>
DIA-07-06 | Production - 6.5.1 Control measures report - 6.5.2 Production process capability report | The Supplier shall share the Functional Safety related sections of their PFMEA and Control Plans. Proof of In-line and EOL testing of Functional Safety related portions of the Element (Pass/Fail criteria demonstrated). Stellantis to approve. The Supplier shall provide to Stellantis complementary Control plans for Stellantis manufactoring process if needed. | [5 empty] | <Name> | <select> |  |  |  | <select>
DIA-07-07 | Operation, service, and decommissioning - 7.5.1 Field observation instructions | The Supplier shall provide to Stellantis any request related sections of the Owner's Manual. The Supplier shall provide to Stellantis any request related sections of the Service/Repair Manual and procedures. The Supplier shall provide to Stellantis any request related Vehicle Information Labeling. Supplier to report comments/improvements. Supplier shall provide Evidence of Field Monitoring and lessons learned management in consistency with Stellantis warranty return policy The Supplier shall provide to Stellantis any related recycling requirements and special handling/disposal requirements. | [5 empty] | <Name> | <select> |  |  |  | <select>
Part 8: Supporting Processes
DIA-08-05 | Interfaces within distributed Developments Note; supplier scope is for the suppliers of the supplier (tier 1+n) - 5.5.1 Supplier selection report - 5.5.2 Development interface agreement (DIA) - 5.5.3 Supplier's safety plan - 5.5.4 Functional safety assessment report - 5.5.5 Supplier agreement | Stellantis shall reserve the right to plan a safety assesment/audit with the supplier | [5 empty] | <Name> | <select> |  |  |  | <select>
DIA-08-06 | Specification and Management of Safety Requirements | [6 empty] | <Name> | <select> |  |  |  | <select>
DIA-08-07 | Configuration Management - 7.5.1 Configuration management plan | [6 empty] | <Name> | <select> |  |  |  | <select>
DIA-08-08 | Change Management - 8.5.1 Change management plan - 8.5.2 Change request - 8.5.3 Impact analysis and change request plan - 8.5.4 Change report | All Supplier work products shall be under change and configuration management and shall be traceable to appropriate requirements specification(s) and aligned with safety plan Supplier shall create/submit a traceability report in each phase of development. After initial safety case is approved, the supplier shall inform the Stellantis safety team of changes not driven by Stellantis functional requirements. These changes could result from quality issues or IC shortages. The supplier shall perform impact analysis and communicate to Stellantis planned updates to safety artifacts. | [5 empty] | <Name> | <select> |  |  |  | <select>
DIA-08-09 | Verification - 9.5.1 Verification plan - 9.5.2 Verification specification - 9.5.3 Verification report | [6 empty] | <Name> | <select> |  |  |  | <select>
DIA-08-10 | Documentation management - 10.5.1 Documentation management plan - 10.5.2 Documentation guideline requirements | [6 empty] | <Name> | <select> |  |  |  | <select>
DIA-08-11 | Confidence in the Use of SW Tools - 11.5.1 Software tool criteria evaluation report - 11.5.2 Software tool qualification report | [6 empty] | <Name> | <select> |  |  |  | <select>
DIA-08-12 | Qualification of SW Components - 12.5.1 Software component documentation - 12.5.2 Software component qualification report - 12.5.3 Software component qualification verification report | [6 empty] | <Name> | <select> |  |  |  | <select>
DIA-08-13 | Evaluation of HW elements - 13.5.1 Hardware element evaluation plan - 13.5.2 Hardware element test plan - 13.5.3 Hardware element evaluation report for hardware elements | [6 empty] | <Name> | <select> |  |  |  | <select>
DIA-08-14 | Proven in Use Argument - 14.5.1 Description of candidate for proven in use argument - 14.5.2 Proven in use analysis reports | [6 empty] | <Name> | <select> |  |  |  | <select>
Part 9: ASIL-oriented and safety-oriented analyses
DIA-09-05 | Requirements decomposition with respect to ASIL tailoring - 5.5.1 Update of architectural information - 5.5.2 Update of ASIL as attribute of safety requirements and elements | [6 empty] | <Name> | <select> |  |  |  | <select>
DIA-09-06 | Criteria for coexistence of elements - 6.5.1 Update of the ASIL attribute of the sub-elements of the element | [6 empty] | <Name> | <select> |  |  |  | <select>
DIA-09-07 | Analysis of dependent failures - 7.5.1 Dependent Failures Analysis - 7.5.2 Dependent Failures Analysis Verification Report | [6 empty] | <Name> | <select> |  |  |  | <select>
DIA-09-08 | Safety analyses - 8.5.1 Safety analyses - 8.5.2 Safety analyses verification report | [6 empty] | <Name> | <select> |  |  |  | <select>
[5 empty] | Stellantis <--- Supplier |  | R | Responsible for activity/deliverable | Yes
|  |  | 1 - Full Version Delivery |  | Stellantis ---> Supplier |  | A | Approves final deliverable | No
|  |  | 2- Short Version Delivery / Summary - Delivery of Synthesis or Relevant Extracted Information |  | Stellantis <--- Supplier |  | S | Supports development of deliverable | Partial
|  |  | 3- Review at Supplier Premise |  | Not Applicable |  | I | Informed (view) final deliverable | Not Applicable
|  |  | 4- Not Applicable |  |  |  | <select> |  | <select>

## Template Overview
Development Interface Agreement (DIA)Template
Proprietary and Confidential
File/Revision | Release Date | Effective Date | Concise Description of Changes
WI_DIA Rev 1.3 | 2015-AUG-14 Draft | TBD | Template created consistent with EE CS.00046 Level 2 Draft for review
SLM_DIA.xlsx | 2017-AUG-08 | 2017-AUG-08 | Template updated for the use in a SOW for component suppliers.
WI_DIAv2.xlsx | 2018-FEB-01 | 2018-FEB-01 | Template updated by Neil & Anthony
WI_DIAv3.xlsx | 2018-OCT-26 | 2018-OCT-26 | Overview - No signatures by D. Smerza
FSD.00001/DIA_v4.xlsx | 2021-MAR-18 | 2021-MAR-18 | Updates to ISO and safety plan format references in DIA worksheet tab completed by Elton Jamoua
FSD.00001/DIA_v5.xlsx (xF) 02016_13_02411 V8 (xP) | 2022-MAY-13 | 2022-MAY-13 | xP & xF DIA Template convergence
FSD.00001/DIA_V6.2.xlsx (xF) | 2023-MAR-27 | 2023-MAR-27 | Removed Template / Work Instruction Column Removed Records & Document Exchange Column Added of deliverable column & deliverable Included Policy and procedure wording for every line item Removed Verification Checklist Tab Removed ‘How to’ previously blank Added Supplier Guidance Tab Removed management of FS for Stellantis Removed ‘partial’ as an agreement option Added DFMEA Risk Reduction Tab Example RASI updated for each line item
Prepared by: |  | Approved by:
Name: Stellantis Functional Safety team Title/Role: Functional Safety network |  | Name: Danette Burns (xF) - Lisa MILLET (xP) Title/Role: Functional Safety Manager / Safety Analysis & Audit
1.0 PURPOSE | This Template provides a project specific mechanism for contractually documenting the required xF Functional SafetyP Work Products (according to CS.00046/xx) and RASI between Stellantis and their Supplier Partners . The DIA shall be first distributed with Stellantis' expectations to potential Suppliers with Quote Packages. Subsequently, the selected Supplier and Stellantis shall negotiate and tailor the final DIA, which shall be maintained by Stellantis throughout the full safety lifecycle
2.0 SCOPE | This Template applies to applications of the xF EE Functional SafetyP at all worldwide Stellantis locations
3.0 REFERENCES | xF EE Functional SafetyP: CS.00046/01 and ISO 26262 (Released, Dec. - 2018) See xF CS.00046 for a full glossary of Terms, Abbreviations and Definitions
4.0 RESPONSIBILTY | The Functional Safety Manager (Functional SafetyM) or his/her delegate is responsible for preparation and maintenance of all DIAs
5.0 TARGET AUDIENCE | The audience of this document includes Program Management, Systems, HW and SW Design & Development Engineers, Systems, HW and SW Validation Engineers, Functional Safety Engineers and Functional Safety Manager at both Stellantis and their selected Suppliers
6.0 INPUTS/PRE-REQUISITES | Item Definition, Safety Plan, HARA, Safety Concept (including Technical Safety Requirements) Impact Analysis (if the new Item is a modification to existing production Item)
7.0 CHANGE MGMT AND IMPACT ANALYSIS | All Work Products called out in this DIA shall be subject to formal change management after 1A Release. Subsequent changes shall require an Impact Analysis (IA) conducted by the Functional Safety Manager. An IA is a review of the proposed change against the existing Safety Plan work products with specific focus given for impact to safety requirements, safety analyses, safety design and validation activities.
9.0 RECORDS/LOGS | The final completed DIA shall be stored per Stellantis record and retention requirements.
Master files are stored electronically. Printed copies are for reference only.

## FMEA Risk
EXAMPLE ONLY

## Scope
SYSTEM
Stellantis SYSTEM
SUPPLIER SYSTEM
OTHER SYSTEMS
HW
SW
HW
SW

## WorkFlow_Basic
Stellantis
Supplier
TBD